## README
REEF RUN — Kickstarter campaign dashboard (11_CAMPAIGN_DASHBOARD.md)
Inputs: copy the goal and planned average pledge from 03_funding_model.xlsx (Scenarios), set the launch date. No cross-file links, on purpose.
Pre-launch: one row per day for the 6 weeks before launch (Kickstarter followers from the pre-launch page, email list, wishlists).
Daily: fill one row per campaign day from the Kickstarter creator dashboard (pledged, backers, cancellations, visits by referrer) and your ad accounts.
Forecast: three cumulative-share curves (yellow, assumptions). Forecast = pledged so far ÷ share of the total a campaign usually has by that day.
Triggers: each row turns red when its condition is met. The response for each is in 11_CAMPAIGN_DASHBOARD.md §4.
Grey italic first row in each log = EXAMPLE. Overwrite it with day 1.

## Inputs
Funding goal (EUR) | 14000 | From 03_funding_model.xlsx → Scenarios, FUNDING GOAL (MVD)
Planned average pledge (EUR) | 37.56 | From 03 → Rewards (blended)
Launch date | 2027-04-13 | Provisional (03 §5). Type a real date.
Campaign length (days) | 30 | Max 30 because of Steam key rules (S3)
Marketing budget for the campaign (EUR) | 1500 | 03 Costs, MVD (live-campaign ads; v2)
Net revenue per backer used to judge ads (EUR) | 28.8 | ≈ average pledge × (1 − 23.3% deductions incl. VAT), from 03 v2
Kickstarter followers at launch (type on launch day) | 0 | From the pre-launch page
Cancellation alert threshold (% of pledged) | 5% | Assumption

## Pre-launch
Days to launch | Date | KS followers (total) | Email subscribers (total) | Steam wishlists (total) | Expected launch backers (followers×20% + email×4%) | Share of goal covered at launch | Notes
42 |  | 310 | 900 | 5200 |  |  | EXAMPLE ROW
41
40
39
38
37
36
35
34
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1

## Daily
Day | Date | Pledged today (EUR) | New backers today | Cancelled today (EUR) | Cancelled backers today | Net pledged (cumulative) | Backers (cumulative) | Funded % | Average pledge | Visits today | Conversion (new backers ÷ visits) | Visits: Kickstarter | Visits: email | Visits: social | Visits: creators/press | Visits: ads | Ad spend today (EUR) | Ad-attributed backers | Ad cost per backer | Days left | Needed per remaining day (EUR) | Notes / what we did
1 |  | 2900 | 101 | 0 | 0 |  |  |  |  | 1650 |  | 700 | 380 | 320 | 150 | 100 | 60 | 2 |  |  |  | EXAMPLE ROW — replace with real day 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Tiers
Tier | Price | Planned mix | Backers (type from KS dashboard) | Pledged | Actual mix | vs plan (points) | Limit | Remaining
Ripple | 5 | 7% | 0
Early Diver | 12 | 18% | 0 |  |  |  | 300
Diver | 15 | 20% | 0
Founding Diver | 29 | 22% | 0
Pod of Four | 49 | 20% | 0
Founding Pod | 99 | 10% | 0
Name the Trawler | 199 | 3% | 0 |  |  |  | 25
No reward / custom | 1 | 0% | 0
Totals
Note on E2: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E3: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E4: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E5: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E6: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E7: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E8: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.
Note on E9: Custom amounts above the tier price aren't captured; use the KS dashboard total for money.

## Forecast
Day | Conservative: cumulative share of final total by this day | Baseline | Optimistic | Forecast final (conservative) | Forecast final (baseline) | Forecast final (optimistic) | Latest forecast
1 | 16.61% | 12.46% | 9.14% |  |  |  | Last filled day
2 | 28.92% | 21.69% | 15.91% |  |  |  | Conservative final pledged
3 | 40% | 30% | 22% |  |  |  | Baseline final pledged
4 | 41.88% | 32% | 24% |  |  |  | Optimistic final pledged
5 | 43.75% | 34% | 26%
6 | 45.63% | 36% | 28% |  |  |  | Curves are assumptions (yellow = the day-3 anchor). Forecasts before day 4 swing wildly; triggers T3/T7 wait for day 4.
7 | 47.5% | 38% | 30%
8 | 49.38% | 40% | 32%
9 | 51.25% | 42% | 34%
10 | 53.12% | 44% | 36%
11 | 55% | 46% | 38%
12 | 56.87% | 48% | 40%
13 | 58.75% | 50% | 42%
14 | 60.62% | 52% | 44%
15 | 62.5% | 54% | 46%
16 | 64.38% | 56% | 48%
17 | 66.25% | 58% | 50%
18 | 68.12% | 60% | 52%
19 | 70% | 62% | 54%
20 | 71.88% | 64% | 56%
21 | 73.75% | 66% | 58%
22 | 75.62% | 68% | 60%
23 | 77.5% | 70% | 62%
24 | 79.37% | 72% | 64%
25 | 81.25% | 74% | 66%
26 | 83.13% | 76% | 68%
27 | 85% | 78% | 70%
28 | 88.6% | 83.27% | 77.19%
29 | 93.85% | 90.99% | 87.71%
30 | 100% | 100% | 100%

## Triggers
# | Trigger | Value now | Threshold | Fired? | Response (11 §4)
T1 | Pre-launch: expected launch backers cover < 30% of goal (latest pre-launch row) |  | 30% |  | Weak pre-launch: postpone launch (11 §4.1)
T2 | Funded % at end of day 2 below 20% |  | 20% |  | Slow first 48 h (11 §4.2)
T3 | Baseline forecast below 100% of goal (from day 4) |  | 100% |  | Funding below expectations (11 §4.5)
T4 | Pledged today < 50% of needed-per-day for 3 days running (latest 3 filled days) |  | 1 |  | Mid-campaign plateau (11 §4.3)
T5 | Cancellations above threshold (% of gross pledged) |  |  |  | Investigate: price, a bad update, card failures
T6 | Ad cost per backer above net revenue per backer |  |  |  | Pause the ads (11 §4)
T7 | Optimistic forecast above 300% of goal (from day 4) |  | 300% |  | Sudden attention (11 §4.4)
T8 | A limited tier sold out (remaining = 0) |  | 1 |  | Say so once in an update; do NOT add another limited tier